## Release <4.6.3> - Status
Project Management Office
Weekly Project Status Report
Report Information
Product |  | IntelliMax |  | Release # | 4.6.3
Prepared by |  | Shahid Rafi (PM - VizMax) Sheraz Pervaiz (PM - CoreMax) Khurram Saeed (STM & PM - DataMax) |  | Reporting Period | 26th to 30th August 2013
New Development
Sr. # | Column1 | Features | Assinged Team(s) | Planned Delivery Date | Phase | Status | Comments
1
2
3 | [6 empty] | Development is completed. Validation is testing the feature.
4
5
6
7 | [6 empty] | Development is completed. Validation is testing the feature.
8
9
11
12
13 | [6 empty] | Bug fixing is in progress
14 | [6 empty] | Validation reported bugs, development fixing bugs
Documentation
Sr. # | TFS Work Item ID | Features | Assinged Team | Phase | Planned Delivery Date | Status | Comments
26484 | 23456 | Easy Caching of Tags | Rehan bin Khalid | Beta Testing | 2013-05-30 | Working/ In Progress
26485 | 23456 | Validate Items | Rehan bin Khalid | Beta Testing | 2013-06-06 | Working/ In Progress
26481 | 23456 | Windows 8 | Sadaf Mufti | Beta Testing | 2013-06-18 | Working/ In Progress
26483 | 23456 | Windows Server 2012 | Sadaf Mufti | Beta Testing | 2013-06-21 | Working/ In Progress
26487 |  | OnTextChange event in Screens | Sadaf Mufti | Beta Testing | 2013-06-28 | Working/ In Progress
26486 | 23456 | Custom Font Support | Rehan bin Khalid | Beta Testing | 2013-06-20 | Working/ In Progress
27454 |  | MySQL Personalization and Version Upgrade | Sadaf Mufti | Beta Testing | 2013-07-10 | Working/ In Progress
26488 |  | JRE 1.7 Upgrade | Rehan bin Khalid | Development | 2013-07-12 | Onhold | 80% work has been completed but stakeholder's decision is required on JRE Update prompt on client launch to complete rest on the work.
26489 |  | Engineering Events | Rehan bin Khalid | Beta Testing | 2013-07-12 | Working/ In Progress
TFS Bug ID | TFS Work Item ID | Bug Titles | Assinged Writer | Phase | Planned Delivery Date | Status | Comments
26865 | 23456 | [MAXv4.6.3_0085.0003][Help]:4.6.3 help should not have 4.7 feature highlights | Rehan bin Khalid | Beta Testing | 2013-08-06 | NotAFix | Targeted for CD 14.
26748 |  | [MAXv4.6.3_0085.0001][DB Repair Utility][help]:Help should be Updated according to New/Modified FS. | Bushra Naz | Beta Testing | 2013-08-05 | Closed
28842 |  | [MAXv4.6.3_0085.0009-R2][F1Linking/User Guide]: Misspelled words highlighter should disable in script editor and help should update in User Guide. | Bushra Naz | Beta Testing | 2013-08-07 | Closed
26716 |  | [MAXv4.6.3_0085.0001][Custom Font Support-UserGuide] Feature of Custom Font Support should be elaborated in Intellimax User guide | Rehan bin Khalid | Beta Testing | 2013-08-07 | Closed
28312 |  | [MAXv4.6.3_0085.0007_R1-CR][Help - User Guide] Help Boomark on Historian Summary tab is not working. | Rehan bin Khalid | Beta Testing | 2013-07-18 | Closed
28885 |  | [MAXv4.6.3_0085.0010][Help]:obsolete Pages should be Removed from Help. | Sadaf Mufti | Beta Testing | 2013-08-06 | Closed
28973 |  | [MAXv4.6.3_0085.0012_R1][Help ]IMAX Help Manuals should be updated for the feature "JRE 1.7 upgrade and Java version independence" | Rehan bin Khalid | Development | 2013-08-26 | Onhold | Same as for 26488
28974 |  | [MAXv4.6.3_0085.0012_R1][Help]IMAX Help Manuals should be updated for the feature "Engineering Events" | Rehan bin Khalid | Beta Testing | 2013-08-23 | Closed
Change Requests
Sr. # | TFS Work Item ID | Change Description | Related Features | Assinged Team | Effort Estimates (Man Hrs.) | Status | Comments
1 |  | Not Applicable
2
3
|  |  | Total |  | 0
Status Summary
Sr. # | Features |  | Status Summary
1
2
3
4
Sr. # | Issue / Risk Description |  | Impact | Mitigation / Corrective Action | Assigned to | Due Date | Current Progress
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Constraints & Dependencies
Sr. #
1
2
3
4
5
6
7
Assumptions
Sr. #
1
2
3
4
5
6
Guideline for Report Preperator:

## Release <4.6.4> - Status
Project Management Office
Weekly Project Status Report
Report Information
Product |  | IntelliMax |  | Release # | 4.6.4
Prepared by |  | Shahid Rafi (PM - VizMax) Sheraz Pervaiz (PM - CoreMax) Kharrum Saeed (STM & PM - DataMax) |  | Reporting Period | 26th to 30th August 2013
New Development
Sr. # | Column1 | Features | Assinged Team(s) | Phase | Planned Delivery Date | Status | Comments
1
2
3
4
5
Documentation
Sr. # | TFS Work Item ID | Features | Assinged Team | Phase | Planned Delivery Date | Status | Comments
1 | 23456 | Client Redundancy | Documentation | Planning | To be established | Estimating | Initial FS Study and DTR activity has been conducted to estimate timelines.
2 | 23456 | Engineering Events - Change Requests | Documentation | Planning | To be established | Estimating | FS Review Activity has been conducted first to resolve conflicts between PMG FS and base-lined FS version and estimate timelines.
3 | 23456
4 | 23456
5 | 23456
Change Requests
Sr. # | TFS Work Item ID | Change Description | Related Features | Assinged Team | Effort Estimates (Man Hrs.) | Status | Comments
1
2
3
|  |  | Total |  | 0
Status Summary
Sr. # | Features |  | Status Summary
1 | 1
2 | 3
Issues & Risks
Sr. # | Issue / Risk Description |  | Impact | Mitigation / Corrective Action | Assigned to | Due Date | Current Progress
1
2
3
4
5
Constraints & Dependencies
Sr. # | Description
1
2
3
4
5
Assumptions
Sr. # | Description
1
2
3
4

## Release <4.7> - Status
Project Management Office
Weekly Project Status Report
Report Information
Product |  | IntelliMax |  | Release # | 4.7
Prepared by |  | Shahid Rafi (PM - VizMax) Sheraz Pervaiz (PM - CoreMax) Kharrum Saeed (STM & PM - DataMax) |  | Reporting Period | 26th to 30th August 2013
New Development
Sr. # | TFS Work Item ID | Features | Assinged Team(s) | Phase | Planned Delivery Date | Status | Comments
1 | 23456
4 | 23456
5 | 23456
6 | 23456
7 | 23456
8 | 23456
Documentation
Sr. # | TFS Work Item ID | Features | Assinged Team | Phase | Planned Delivery Date | Status | Comments
1 | 23456 | Farsi Calendar | Documentation | Planning | To be established | Not yet Started
2 | 23456 | Tableau | Documentation | Planning | To be established | Not yet Started
3 | 23456 | DataGrid | Documentation | Planning | To be established | Not yet Started
5 | 23456
Change Requests
Sr. # | TFS Work Item ID | Change Description | Related Features | Assinged Team | Effort Estimates (Man Hrs.) | Status | Comments
1 | 23456
3
4
5
|  |  | Total |  | 0
Status Summary
Sr. # | Features |  | Status Summary
1 | Farsi Calendar |  | Development team is in process of finishing the 2nd cut of Farsi Calendar, Negotiating new requirements, estimating timelines for changes in requirements and fixing bugs for the first cut.
2
3
4
Issues & Risks
Sr. # | Issue / Risk Description |  | Impact | Mitigation / Corrective Action | Assigned to | Due Date | Current Progress
2 | Trend Sampling Issue (Tech Support # 26890) |  | To be established | To be established | To be established | To be established
3
4
5
6
Constraints & Dependencies
Sr. # | Description
1 | Not Applicable
2
3
4
5
6
Assumptions
Sr. # | Description
1 | Not Applicable
2
3
4
5
6

## Release <4.8> - Status
Project Management Office
Weekly Project Status Report
Report Information
Product |  | IntelliMax |  | Release # | 4.8
Prepared by |  | Shahid Rafi (PM - VizMax) Sheraz Pervaiz (PM - CoreMax) Khurram Saeed (STM & PM - DataMax) |  | Reporting Period | 26th to 30th August 2013
New Development
Sr. # | Column1 | Features | Assinged Team(s) | Phase | Planned Delivery Date | Status | Comments
1 | [7 empty] | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4 | 1 | DataMAX Redesign Phase 1 | DataMax | Development | On Hold | Team working on 4.6.3 and 4.6.4
Documentation
Sr. # | Column1 | Features | Assinged Team | Phase | Planned Delivery Date | Status | Comments
1 |  | DataMAX Redesign | Documentation | Planning | Not yet Started
Change Requests
Sr. # | Column1 | Change Description | Related Features | Assinged Team | Effort Estimates (Man Hrs.) | Status | Comments
1
2
3
4
5
|  |  | Total |  | 0
Status Summary
Sr. # | Features |  | Status Summary
1
2
Issues & Risks
Sr. # | Issue / Risk Description |  | Impact | Mitigation / Corrective Action | Assigned to | Due Date | Current Progress
1
Constraints & Dependencies
Sr. # | Description
Assumptions
Sr. # | Description

## Release <4.7> - Statistics (hidden)
Project Management Office
Weekly Release Status Report
Overall Release Progress
| Values | Analysis Comments
Planned Release Completion Date : | 2013-09-19
Projected Release Completion Date : | 2013-09-23
Finish Variance or Delay (Days) : | 5 Days
Duration Statistics | Duration Values | Effort Statistics | Effort Values
Release Baseline Duration (Days) : | 100 | Release Baseline Effort (Hrs) : | 800
Overall Duration Complete (%): | 15% | Overall Effort Complete (%): | 15%
Baseline Duration to this Week (Hrs) : | 15 | Baseline Effort upto this Week (Hrs) : | 120
Actual Duration Spent to this Week(Days) : | 16 | Actual Effort Spent upto this Week (Hrs) : | 130
Release Projected Duration (Days) : | 101 | Release Projected Effort (Hrs) : | 810
Release Variances | Variance Values | Threshold Limits | Analysis Comments | Corrective Action
Finish Variance or Delay (Days) : | 5 | <=10% & <=4 days
Duration Variance (%) | 6.667% | 10%
Effort Variance (%) | 8.333% | 15%
Note on B9: Enter the Last "Baseline Finish" date for the Project from PS
Note on B10: Enter the "Finish" date for the Project from PS
Note on B11: Enter "Finish Variance" for the Project from PS
Note on B14: Enter the "Baseline Duration" for the Project from PS
Note on D14: Enter the Last "Baseline Work" for the Project from PS
Note on B15: Enter the "% Complete" for the Project from PS
Note on D15: Enter the "% Work Complete" for the Project from PS
Note on B16: Baseline Duration So Far = (% Duration Complete * Overall Baseline Duration)
Note on C16: Auto calculated
Note on D16: Baseline Effort So Far = (% Effort Complete * Overall Baseline Effort)
Note on E16: Auto calculated
Note on B17: Enter the "Actual Duration" for the Project from PS
Note on D17: Enter the "Actual Work" for the Project from PS
Note on B18: Enter the "Duration" for the Project from PS
Note on D18: Enter the "Duration" for the Project from PS
Note on B21: Enter "Finish Variance" for the Project from PS
Note on D21: Limit: FV should not be greater than 4 days or 10 % of the baseline duration.
Note on B22: DV = [(Acual Duration - Baseline Duration So far) / Baseline Duration So far] * 100
Note on D22: Limit: DV should not be greater than 10%
Note on B23: EV = [(Acual Effort - Baseline Effort So far) / Baseline Effort So far] * 100
Note on D23: Limit: EV should not be greater than 15%

## Production Issues
Project Management Office
Weekly Project Status Report
Production Issues (Since 15th June 2013)
Sr. # | TFS Work Item ID | Issue Description | Assinged Team | Effort (Man Hrs.) | Impacted Features | Impact Release | Status | Comments
1
2
3
4
5
0

## Month dd, yyyy (hidden)
Enterprise Quality Management System
Weekly Project Status Report
Project Overview
| #REF! | PMG
| PM | Shahid Rafi
| Report for Week Ending | 2013-06-07
| Planned Project Completion Date | 2013-06-13
| Projected Project Completion Date: | 2013-06-13
| Project Baseline for which status report is prepared | CD No : 4.6.3 -7
Schedule Variance - Project Level
Sr. | Report for Week Ending | Total Planned Project Duration | Baseline for the Reporting Week | Projected Project Duration | % Complete for Project | Planned Project Duration as per % complete | Actual Duration of Project | SV - Project | Target | USL | LSL
1 | 2007-08-24 | 180 | Baseline 1 | 184 | 20% | 36 | 40 | 11.11% | 0% | 8% | -8%
2 | 2007-08-31 | 180 | Baseline 1 | 184.998 | 23.89% | 43.002 | 48 | 11.62% | 0% | 8% | -8%
3 | 2007-09-07 | 180 | Baseline 1 | 188.996 | 27.78% | 50.004 | 59 | 17.99% | 0% | 8% | -8%
4 | 2007-09-14 | 190 | Baseline 2 | 190.827 | 31.67% | 60.173 | 61 | 1.374% | 0% | 8% | -8%
5 | 2007-09-21 | 180 | Baseline 3 | 183.992 | 35.56% | 64.008 | 68 | 6.237% | 0% | 8% | -8%
6 | 2007-09-28 | 180 | Baseline 3 | 183.99 | 39.45% | 71.01 | 75 | 5.619% | 0% | 8% | -8%
7 | 2007-10-05 | 180 | Baseline 3 | 177.988 | 43.34% | 78.012 | 76 | -2.579% | 0% | 8% | -8%
8 | 2007-10-12 | 180 | Baseline 3 | 179.986 | 47.23% | 85.014 | 85 | -0.01647% | 0% | 8% | -8%
Effort Variance - Project Level
Sr. | Report for Week Ending | Total Planned Project Effort | Baseline for the Reporting Week | Projected Project Effort | % Work Complete for Project | Planned Project Effort as per % Work Complete | Actual Project Effort Spent: | EV - Project | Target | USL | LSL
1 | 2007-08-24 | 4890 | Baseline 1 | 4965.3 | 23% | 1124.7 | 1200 | 6.695% | 0% | 10% | -10%
2 | 2007-08-31 | 4890 | Baseline 1 | 4918.6 | 26% | 1271.4 | 1300 | 2.249% | 0% | 10% | -10%
3 | 2007-09-07 | 4890 | Baseline 1 | 4921.9 | 29% | 1418.1 | 1450 | 2.249% | 0% | 10% | -10%
4 | 2007-09-14 | 5000 | Baseline 2 | 5000 | 32% | 1600 | 1600 | 0% | 0% | 10% | -10%
5 | 2007-09-21 | 5500 | Baseline 3 | 5475 | 35% | 1925 | 1900 | -1.299% | 0% | 10% | -10%
6 | 2007-09-28 | 5500 | Baseline 3 | 5350 | 38% | 2090 | 1940 | -7.177% | 0% | 10% | -10%
7 | 2007-10-05 | 5500 | Baseline 3 | 5245 | 41% | 2255 | 2000 | -11.31% | 0% | 10% | -10%
8 | 2007-10-12 | 5500 | Baseline 3 | 5580 | 44% | 2420 | 2500 | 3.306% | 0% | 10% | -10%
Note on D7: Auto-generated
Note on D8: Auto-generated
Note on C15: Enter the Last date of the week for which this report is prepared
Note on D15: Enter the days from the latest Baseline Duration column of PS
Note on F15: Enter the days from Duration column of PS
Note on G15: Enter the percentage from % Complete column of PS
Note on H15: Auto-calculated This gives the duration which was planned to be completed for the Project according to % completion
Note on I15: Enter the days from Actual Duration column of PS
Note on J15: Auto-calculated
Note on L15: Upper Specification Limit
Note on M15: Lower Specification Limit
Note on O15: Enter the RCA ID from the RCA Workbook
Note on P15: Enter the identified Root Cause from the RCA Workbook
Note on C56: Enter the Last date of the week for which this report is prepared
Note on D56: Enter the Man hrs from latest Baseline Work column of PS
Note on F56: Auto-calculated/ Enter the Man hrs from Work column of PS
Note on G56: Enter the percentage from % Work Complete column of PS
Note on H56: Auto-calculated This gives the effort which was planned to be spent on the Project according to % work completion
Note on I56: Enter the Actual effort (billable) spent on the whole Project from Time Sheet
Note on J56: Auto-calculated
Note on L56: Upper Specification Limit
Note on M56: Lower Specification Limit
Note on O56: Enter the RCA ID from the RCA Workbook
Note on P56: Enter the identified Root Cause from the RCA Workbook
Note on C95: List down the phases/ milestones for the project here. In case of incremental SDLC: Phases for each increment should be listed here. For example: Testing Release 1 Testing Release 2 (All project Phases will be listed here)
Note on D95: Enter the days from latest Baseline Duration column of PS if the phase is not complete. In case the phase is complete then enter the days from the Baseline Duration column with which the phase was completed.
Note on F95: Enter the days from Duration column of PS
Note on G95: Enter the percentage from % Complete column of PS
Note on H95: Auto-calculated This gives the duration which was planned to be completed for the Phase according to % completion
Note on I95: Enter the days from Actual Duration column of PS
Note on J95: Auto-calculated
Note on L95: Upper Specification Limit
Note on M95: Lower Specification Limit
Note on O95: Enter the RCA ID from the RCA Workbook
Note on P95: Enter the identified Root Cause from the RCA Workbook
Note on C138: List down the phases/ milestones for the project here. In case of incremental SDLC: Phases for each increment should be listed here. For example: Testing Release 1 Testing Release 2 (All project Phases will be listed here)
Note on D138: Enter the days from latest Baseline Work column of PS if the phase is not complete. In case the phase is complete then enter the days from the Baseline Work column with which the phase was completed.
Note on F138: Auto-calculated
Note on G138: Enter the percentage from % Work Complete column of PS
Note on H138: Auto-calculated This gives the effort which was planned to be spent on the Phase according to % work completion
Note on I138: Enter the Actual effort (billable) spent on the phase from Time Sheet
Note on J138: Auto-calculated
Note on L138: Upper Specification Limit
Note on M138: Lower Specification Limit
Note on O138: Enter the RCA ID from the RCA Workbook
Note on P138: Enter the identified Root Cause from the RCA Workbook
Note on C178: Lsit down the Milestones of the project as per defined in Project Management Plan
Note on D178: Enter the Baseline Finish date for the task from PS
Note on E178: Enter the Finish date for the task from PS
Note on F178: Enter the Actual Finish date for the task from PS
Note on C184: Please List down all the deliverables/ Tasks of the week from PS. In case the no. of tasks is very high, group task of those tasks can be listed here. For help, a report can be generated from the PS containing the tasks for a week. (Views/Reports/Current Activities) Note: Umbrella activities may not be listed here.
Note on D184: Enter the percentage of the task planned to be completed by the end of the week
Note on E184: Enter the % Complete for the task from PS
Note on F184: Auto-Calculated. This gives the variance of actual progress from planned progress of each deliverable/task for the week
Note on G184: Enter the Baseline Finish date for the task from PS
Note on H184: Enter the Finish date for the task from PS
Note on I184: Enter the Actual Finish date for the task from PS
Note on K184: Enter the Baseline Work for the task from PS
Note on L184: Auto-calculated
Note on M184: Enter the % Work Complete for the task from PS
Note on N184: Auto-Calculated. This gives the effort which was planned to be spent on the task according to % work completion
Note on O184: Enter the Actual effort (billable) spent on the task from Time Sheet
Note on P184: Auto-Calculated. This gives the variance of actual effort from planned effort for each deliverable/task
Note on Q184: Enter the this value for each task from "Critical" column of PS
Note on C190: Don’t list down the risks which were mitigated to closure (the risk whose exposure was '0') in the previous status report.
Note on F190: Auto-Calculated. Product of Probability and Impact.
Note on C218: Please List down all the deliverables/ Tasks for the next week from PS. In case the no. of tasks is very high, group task of those tasks can be listed here. For help, a report can be generated from the PS containing the tasks for a week. [Views/Reports/Current Activities. Should Have Started Task (start by = Next week Starting Date)]

## Architects
Project Management Office
Weekly Project Status Report
Architects Deliverables
Sr. # | TFS Work Item ID | Deliverable | Assigned Architect(s) | Effort Estimates (Man Hrs.) | Start Date | Due Date | Actual Completion Date | Status | Comments / Progress Summary
1
2
3
4
5
6
7
8
9
10
11
12
13
Code Reviews (CA)
Sr. # | TFS Work Item ID | Feature | Assigned Architect(s) | No. of Code Reviews Performed | Status | Comments / Progress Summary
4
1
8
10
11
2
5
6
9
7
3
12
13
14
15
16
17
18
19
20
21
0